University of Florida College of Dentistry

Timeline/Key Tasks for

2017 Strategic Planning Process

April, 2017

- Collect and review past planning and other relevant materials from the College, UF Health and UF.

- Finalize and distribute planning process timeline.

- Identify data requirements for the process and sources for trends analysis/environmental scan and other relevant state and national data. Begin data collection.

- Develop preliminary themes and goals for discussion purposes.

- Plan and develop agendas for initial meetings with SP Steering Committee and four designated Working Groups.

- Prepare and launch web-based internal survey for faculty, students, residents and staff.

- Analyze feedback from internal web-based survey.

May, 2017

- Conduct initial meetings with SP Steering Committee and four designated Working Groups. Share trends analysis data.

- Conduct interviews with key UF stakeholders.

- Draft and launch web-based external survey for alumni and other external audiences.

June – July, 2017

- Organize and conduct initial town hall/open forum sessions for faculty, research faculty, students/residents, practicing clinicians, Dental Advisory Board, and/or other designated audiences.

- Continue meetings with SP Steering Committee and four designated Working Groups.

- Continue town hall/open forum sessions.

- Analyze feedback from external web-based survey.

- Review and discuss recommendations from SP Steering Committee and four designated Working Groups.

August - December, 2017

- Consolidate and analyze all data reviewed and input collected, including recommendations from SP Steering Committee and four designated Working Groups.

- Develop first draft Strategic Plan.  Following review by Dean, circulate to the Steering Committee.

- Draft Strategic Plan updated as indicated, circulate to the Strategic Planning Committee and others for comment.

- Draft Strategic Plan updated, posted online for Faculty Assembly comment.

- Draft Strategic Plan updated, distributed to UF Health and UF administration for comment.

- Draft Strategic Plan finalized for production.

(Note: The timeline will be updated on a periodic basis as needed to adjust tasks, activities, and scheduling.)

---

4/19/17